## Sheet1
Goldsmiths University |  | Final Year Project Gantt Chart
• How many days • Due date | Milestone | Year 2019 | [15 empty] | Year 2020
|  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Review | Project Specification | bar: September W1 to September W2
Gantt Chart | bar: September W2
Market Study UML Diagram | bar: September W3
Use Case Diagram Sequence Diagram | bar: September W4
Prototype | Prototype
Prototype Survey
Backlog & Kanban
Building & Draft Write Up | Front End of The Project
User Testing
Testing Plan
System Testing
Interim Report | bar: January W2
Draft Report | bar: March W4
Viva | Presentation Final Report | bar: May W3